## Sheet1
2022-10-10
What we did well
We submitted project proposal revisions quickly after feedback from the professor was received.
We were able to get Milestone 1 submitted on time.
We did good on the BRD content.
We did decent getting feedback from the professor for our documents.
What we didn't do well
We did not follow Scrum as closely as the professor would have liked. Not much documentation was on our GitHub resulting in a low Team Review 1 evaluation.
We spent too much time on project proposal revisions.
We ONLY worked on the project proposal revisions and did not make much progress on Milestone 1 documents while waiting for approval.
Near the end of the Milestone 1 sprint we had to crunch out hours for our documents because of this.
Action plan to address what we didn't do well
We should more clearly establish what we specifically need first before filling in document content. We will try to parallelize work for all Milestone 2 documents and get feedback from the professor during the next 3 weeks of office hours for each work item we make progress on.
When contributing to logging chat, we will additionally note the amount of productive hours we have done. This will make it easier for the Scrum Master to manage things like the burndown chart.
We will add these documents to GitHub and keep updated regularly to ensure we are following Scrum:
Update everyday is ideal, but at minimum whenever we finish drafts and submissions.
-Project Backlog document (only changes if client tells you to)
-Logging document containing all content from our logging chat in Discord
-Burndown charts to visually represent hours (Jira has a feature for this)
-Daily Standups
-Retrospectives
-Document any weaknesses whenever productivity tanks